## Sheet1
DATE | START | STOP | INTERVAL | Odyssey matrix test | Description
2019-06-05 | 9:30 | 12:30 | 3:00 | Setup | a) Print out test requirements. b) Install Microsoft Visual C++ Redistributable for Visual Studio 2015, 2017 and 2019. c) Install Microsoft Visual Studio 2019 Professional (trial). d) Download 2014-12-01-CEC Software Architecture Materials by Jacob Beningo. e) Setup GetHub repository.
| 14:00 | 19:00 | 5:00 | Review | a) Odyssey requirements. b) C++ class generation. Introduction to C++ from edX. c) matrix operations. Matrix Algebra for Engineers on coursera.
2019-06-06 | 13:00 | 15:30 | 2:30 | Design | a) Customer requirements document.
2019-06-07 | 10:00 | 12:00 | 2:00 | Design | b) Software Requirements Specification document.
| 15:00 | 20:00 | 5:00 | Design | b) Software Requirements Specification document.
2019-06-08 | 12:30 | 16:00 | 3:30 | Design | b) Software Requirements Specification document.
| 16:00 | 18:00 | 2:00 | Design | c) Software Unit Test document.
2019-06-09 | 13:00 | 14:45 | 1:45 | Peer review | Ted Brown reviewed Odyssey-Software_Requirements_Specifications.pdf and Software_Unit_Tests.pdf. He provided Review_FRPjr.txt with comments. I responded with Review_FPJr_to_TB-v1.txt.
| 17:00 | 20:00 | 3:00 | Design | b) Software Requirements Specification document. Revisions from peer review
2019-06-10 | 12:00 | 13:00 | 1:00 | Design | c) Software Unit Test document. Revisions from peer review
| 13:00 | 16:30 | 3:30 | Design | c) Software Unit Test document. Revisions from peer review
| 18:00 | 19:15 | 1:15 | Design | c) Software Unit Test document. Revisions from peer review
2019-06-11 | 13:00 | 19:00 | 6:00 | Implementation | OSR_matrix.h, OSR_matrix.cpp, Odyssey_matrix.cpp
2019-06-12 | 9:00 | 17:00 | 8:00 | Implementation | OSR_matrix.h - constructors, destructor, overloaded set_element(), overloaded get_element(). Odyssey_matrix.cpp - test of overloaded set_element() and overloaded get_element().
2019-06-13 | 9:00 | 18:00 | 9:00 | Implementation | OSR_matrix.h - Reworked overloaded set_element(), overloaded get_element(). OSR_matrix.cpp - Put in all functions from OSR_matrix.h. Added overloaded operator= and overloaded operator+=. Odyssey_matrix.cpp - test of overloaded operator= and overloaded operator+=.
2019-06-14 | 10:30 | 13:30 | 3:00 | Implementation | OSR_matrix.h - Added overloaded operator* (scalar). OSR_matrix.cpp - Added overloaded operator* (scalar). Odessey_matrix.cpp - Test for overloaded operator* (scalar).
| 15:00 | 19:00 | 4:00 | Design | Overloaded operator* (matrix).
| 19:00 | 20:30 | 1:30 | Implementation | OSR_matrix.h - Added overloaded operator* (matrix). OSR_matrix.cpp - Added overloaded operator* (matrix).
2019-06-15 | 12:00 | 13:00 | 1:00 | Design | Overloaded Function Transpose.
| 13:00 | 20:30 | 7:30 | Implementation | OSR_matrix.h - Overloaded Function Transpose. OSR_matrix.cpp - Overloaded Function Transpose. Odessey_matrix.cpp - Test for Overloaded Function Transpose.
2019-06-16 | 10:00 | 12:00 | 2:00 | Documentation | SRS and Unit Test
| 14:00 | 18:00 | 4:00 | Documentation | SRS and Unit Test

## Sheet2
9:30 | 930 | 1230 | 300
14:00 | 1400 | 1900 | 500
13:00 | 1300 | 1530 | 230
10:00 | 1000 | 1200 | 200
15:00 | 1500 | 2000 | 500
12:30 | 1230 | 1600 | 370
16:00 | 1600 | 1800 | 200
13:00 | 1300 | 1445 | 145
17:00 | 1700 | 2000 | 300
12:00 | 1200 | 1300 | 100
13:00 | 1300 | 1630 | 330
18:00 | 1800 | 1915 | 115
13:00 | 1300 | 1900 | 600
9:00 | 900 | 1700 | 800
9:00 | 900 | 1800 | 900
10:30 | 1030 | 1330 | 300
15:00 | 1500 | 1900 | 400
19:00 | 1900 | 2030 | 130
12:30 | 1230
19:00 | 1900
15:30 | 1530
12:00 | 1200
20:00 | 2000
16:00 | 1600
18:00 | 1800
14:45 | 1445
20:00 | 2000
13:00 | 1300
16:30 | 1630
19:15 | 1915
19:00 | 1900
17:00 | 1700
18:00 | 1800
13:30 | 1330
19:00 | 1900
20:30 | 2030